## Project_Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | TIAGo Group5 Project |  | Completed | on time, have a plan | Late, but have a plan | Late/ project at risk
Enter Company Name in cell B2. | Cranfield University
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  | 2022-02-28
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  |  |  | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-02-28 to 2022-05-15
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | Status | Comments | DAYS | time axis 2022-02-28 to 2022-05-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | System Preparation | All Team | 98.57% | 2022-02-28 | 2022-03-14 | C |  | 15
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Install Ubuntu | Balaji V. | 100% | 2022-02-28 | 2022-03-04 | C |  | 5
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 90% | 2022-02-28 | 2022-03-04 | C | Wi-fi problem, able to connect with just one network. IT does not support Linux
|  | Krishna K. | 100% | 2022-02-28 | 2022-03-04 | C |  | 5
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 80% | 2022-02-28 | 2022-03-04 | C | Able to connect just using Ethernet | 5
|  | Manideep R. | 100% | 2022-02-28 | 2022-03-04 | C |  | 5
|  | Shuhua C. | 100% | 2022-02-28 | 2022-03-04 | C
|  | Sudhanshu U. | 100% | 2022-02-28 | 2022-03-04 | C
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Install ROS | Balaji V. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Krishna K. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
|  | Manideep R. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
|  | Shuhua C. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Sudhanshu U. | 100% | 2022-02-28 | 2022-03-07 | C
| Complete ROS Course (Complete Beginier Level) http://wiki.ros.org/ROS/Tutorials | Balaji V. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Jonathan A. | 100% | 2022-02-28 | 2022-03-07 | C | Finished Ros Wiki and ETH Zurich Lectures
|  | Krishna K. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Kshitij R. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Manideep T. | 100% | 2022-02-28 | 2022-03-07 | C
|  | Shuhua C. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
|  | Sudhanshu U. | 100% | 2022-02-28 | 2022-03-07 | C |  | 8
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Literature Review |  | 94.29% | 2022-03-01 | 2022-03-14 | C |  | 14
| 1.2.1 Robot Platform 1.3.1 Navigation | Balaji V. | 100% | 2022-03-01 | 2022-03-11 | C |  | 11
| 1.2.2 Hardware Review 1.3.3 HRI | Jonathan A. | 100% | 2022-03-01 | 2022-03-11 | C |  | 11
| 1.1.3 Smart Cities 1.3.1 Navigation | Krishna K. | 100% | 2022-03-01 | 2022-03-11 | C |  | 11
| 1.1.2 Milton Keynes Hotel 1.3.4 Speech Recognition | Kshitij R. | 80% | 2022-03-01 | 2022-03-11 | C | Late submission. Team could not review information properly. 16.03.22: Correct report section per Mr.Tang feedback
| 1.2.3 Software Review 1.3.3 HRI | Manideep R. | 100% | 2022-03-01 | 2022-03-11 | C
| 1.2.3 Software Review 1.3.2 Object Detection | Shuhua C. | 100% | 2022-03-01 | 2022-03-11 | C |  | 11
| 1.1.1 Milton Keynes Staduim 1.2.3 Object Detection | Sudhanshu U. | 80% | 2022-03-01 | 2022-03-11 | C | Late submission. Team could not review information properly. 16.03.22: Correct report section per Mr.Tang feedback | 11
Sample phase title block | System. Definition | All Team | 71.79% | 2022-03-11 | 2022-03-18 | C |  | 8
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 1. Site review and sytem concept discussion | Balaji V. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-11 | 2022-03-14 | C
|  | Krishna K. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
|  | Manideep R. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
|  | Shuhua C. | 100% | 2022-03-11 | 2022-03-14 | C
|  | Sudhanshu U. | 0% | 2022-03-11 | 2022-03-14 | R | No contribution.Did not assist to meeting
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 2. Stake holders and Concept definition | Balaji V. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-11 | 2022-03-14 | C
|  | Krishna K. | 0% | 2022-03-11 | 2022-03-14 | R | No contribution.Did not assist to meeting | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
|  | Manideep R. | 100% | 2022-03-11 | 2022-03-14 | C |  | 4
|  | Shuhua C. | 100% | 2022-03-11 | 2022-03-14 | C
|  | Sudhanshu U. | 0% | 2022-03-11 | 2022-03-14 | R | No contribution.Did not assist to meeting
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 3. Function Analysis and System Architecture definition | Balaji V. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Matlab Architecture File | 2
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Matlab Architecture File
|  | Krishna K. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Systems theory report section | 2
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-15 | 2022-03-16 | R | Statement of requirements | 2
|  | Manideep R. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Systems theory report section | 2
|  | Shuhua C. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Matlab Architecture File
|  | Sudhanshu U. | 100% | 2022-03-15 | 2022-03-16 | C | Complete Systems theory report section
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 4. System Statetemen of Requirements Definition (Each sub-team to complete its portion) | Balaji V. | 30% | 2022-03-18 | 2022-03-30 | Y |  | 13
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 30% | 2022-03-18 | 2022-03-30 | Y | Shared file to complete SOR.
|  | Krishna K. | 30% | 2022-03-18 | 2022-03-30 | Y |  | 13
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 30% | 2022-03-18 | 2022-03-30 | Y |  | 13
|  | Manideep R. | 30% | 2022-03-18 | 2022-03-30 | Y |  | 13
|  | Shuhua C. | 30% | 2022-03-18 | 2022-03-30 | Y
|  | Sudhanshu U. | 30% | 2022-03-18 | 2022-03-30 | Y
Sample phase title block | System. Detailed Design | All Team | 74.29% | 2022-03-18 | 2022-03-22 | Y |  | 5
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Milestone TIAGo Start up & Basic trainning: 1. How to properly start up & shut down TIAGo Platform. 2. WebGUI connection procedure and actions. 3. Joystick Manipulation. | Balaji V. | 100% | 2022-03-18 | 2022-03-22 | C |  | 5
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-18 | 2022-03-22 | C
|  | Krishna K. | 100% | 2022-03-18 | 2022-03-22 | C |  | 5
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-18 | 2022-03-22 | C |  | 5
|  | Manideep R. | 100% | 2022-03-18 | 2022-03-22 | C |  | 5
|  | Shuhua C. | 100% | 2022-03-18 | 2022-03-22 | C
|  | Sudhanshu U. | 100% | 2022-03-18 | 2022-03-22 | C
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Milestone TIAGo connection to physical Robot. 1. Connect with physical Robot. 2. Perfom movements/speech/recognition/navigation related to system area using terminal or GUI. 3. Deploy Package to simulation with generic program related to your development area | Balaji V. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a publisher / subscriber node | 7
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a publisher / subscriber node
|  | Krishna K. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a publisher / subscriber node | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a TTS package | 7
|  | Manideep R. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a publisher / subscriber & Server and client node | 7
|  | Shuhua C. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a publisher / subscriber node
|  | Sudhanshu U. | 100% | 2022-03-22 | 2022-03-28 | C | Deployed a TTS package
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Milestone 4.Create program & package to run in physical robot as in the Hotel. 5. Test in simulation 6. Deployment on robot | Balaji V. | 100% | 2022-03-29 | 2022-04-07 | C | Package Tested and deployed in robot | 10
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot
|  | Krishna K. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot | 17
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot | 17
|  | Manideep R. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot | 17
|  | Shuhua C. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot
|  | Sudhanshu U. | 100% | 2022-03-29 | 2022-04-14 | C | Package Tested and deployed in robot
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Milestone 3.Integrate programs | Balaji V. | 100% | 2022-04-14 | 2022-04-28 | C |  | 15
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. |  | Jonathan A. | 100% | 2022-04-14 | 2022-04-28 | C
|  | Krishna K. | 100% | 2022-04-14 | 2022-04-28 | C |  | 15
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. |  | Kshitij R. | 0% | 2022-04-14 | 2022-04-28 | R | Not integrated into main program due to late completion. | 15
|  | Manideep R. | 100% | 2022-04-14 | 2022-04-28 | C |  | 15
|  | Shuhua C. | 100% | 2022-04-14 | 2022-04-28 | C
|  | Sudhanshu U. | 0% | 2022-04-14 | 2022-04-28 | R | Not integrated into main program due to late completion.
| System. Testing | All Team | 0% | 2022-04-04 | 2022-05-12 | C
| Task 1 |  | 0% | 2022-03-15 | 2022-03-14 |  |  | 0
| Task 2 |  | 0% | 2022-02-28 | 2022-03-04 |  |  | 5
| Task 3 |  | 0% | 2022-02-28 | 2022-03-04 |  |  | 5
| Task 4 |  | 0% | 2022-02-28 | 2022-03-04 |  |  | 5
| Task 5 |  | 0% | 2022-02-28 | 2022-03-04 |  |  | 5
Sample phase title block | System. Implementation | All Team | 0% | 2022-05-05 | 2022-05-12 | G |  | 8
| Task 1 |  |  | date | date |  |  | #VALUE!
| Task 2 |  |  | date | date |  |  | #VALUE!
| Task 3 |  |  | date | date |  |  | #VALUE!
| Task 4 |  |  | date | date |  |  | #VALUE!
| Task 5 |  |  | date | date |  |  | #VALUE!
`
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Formulas:
Late, but have a plan = [on time, have a plan]+4
Today
Deadline

## List (hidden)
Status | Members
| All Team | Pal Robotics Password:
C | Balaji V. | Group5TIAGo
G | Jonathan A.
Y | Krishna M.
R | Kshitij R.
Manideep T.
Shuhua C.
Sudhanshu U.

## Attendance
Attendance |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held | [5 empty] | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Did not assist | No meeting held |  |  |  | Assisted | Assisted late (past 15 min.) | Very late (past 45 min.) | Did not assist | No meeting held | [6 empty] | Assisted | Assisted late (past 15 min.) | Very late (past 45 min.) | Did not assist | No meeting held
Meeting Date | March | [33 empty] | April | [32 empty] | May
| Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Mon | Tues | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 14-Mar-22 Hotel Visit | 2022-03-14 | 2022-03-15 | 3/15/2022 7:00 p.m. | [49 empty] | 2022-05-03 |  | 2022-05-04 |  | 2022-05-05 |  | 2022-05-06 |  | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | time axis 2022-03-16 to 2022-05-02
[19 empty] | 2022-05-02: Report sesion | Lab Session | Report sesion | Lab Session | Report sesion | Lab Session | Report sesion | Lab Session | Report sesion | Lab Session
Attendee
Balaji Vedal | 72:00 | 3 | 2 | 1 | 3 |  |  | 3 | 0 | 3 |  | 3 |  | 3 | 3 | 2 | 3 | 3 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 2; 2022-04-11: 2; 2022-04-12: 2; 2022-04-14: 2; 2022-04-19: 2; 2022-04-20: 2; 2022-04-21: 1; 2022-04-22: 1; 2022-04-25: 1; 2022-04-26: 3; 2022-04-27: 3; 2022-04-28: 2; 2022-04-29: 3; 2022-05-02: 4 | 1 | 3 | 3 | 3 | 3 | 4 | 1 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0
Jonathan Arreola | 72:00 | 3 | 3 | 2 | 3 |  |  | 3 | 0 | 3 |  | 3 |  | 3 | 3 | 2 | 3 | 3 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 3; 2022-04-11: 3; 2022-04-12: 3; 2022-04-14: 3; 2022-04-19: 3; 2022-04-20: 3; 2022-04-21: 1; 2022-04-22: 3; 2022-04-25: 3; 2022-04-26: 3; 2022-04-27: 3; 2022-04-28: 2; 2022-04-29: 1; 2022-05-02: 3 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0
Krishna Keshav | 3 | 3 | 2 | 3 | 3 |  |  | 3 | 0 | 3 |  | 3 |  | 3 | 3 | 1 | 3 | 3 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 1; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 2; 2022-04-11: 2; 2022-04-12: 2; 2022-04-14: 1; 2022-04-19: 2; 2022-04-20: 2; 2022-04-21: 2; 2022-04-22: 1; 2022-04-25: 2; 2022-04-26: 3; 2022-04-27: 3; 2022-04-28: 2; 2022-04-29: 1; 2022-05-02: 4 | 1 | 3 | 3 | 4 | 3 | 4 | 1 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0
Kshitij Raje | 3 | 3 | 2 | 1 | 2 |  |  | 1 | 0 | 3 |  | 1 |  | 3 | 3 | 3 | 1 | 1 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 2; 2022-04-06: 3; 2022-04-08: 2; 2022-04-11: 2; 2022-04-12: 1; 2022-04-14: 1; 2022-04-19: 1; 2022-04-20: 2; 2022-04-21: 1; 2022-04-22: 1; 2022-04-25: 1; 2022-04-26: 2; 2022-04-27: 3; 2022-04-28: 1; 2022-04-29: 1; 2022-05-02: 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 0 | 0 | 4 | 3 | 2 | 3 | 0
Manideep Reddy | 3 | 3 | 2 | 3 | 3 |  |  | 3 | 0 | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 3; 2022-04-11: 3; 2022-04-12: 3; 2022-04-14: 3; 2022-04-19: 3; 2022-04-20: 2; 2022-04-21: 2; 2022-04-22: 3; 2022-04-25: 3; 2022-04-26: 2; 2022-04-27: 3; 2022-04-28: 3; 2022-04-29: 1; 2022-05-02: 4 | 3 | 2 | 3 | 1 | 1 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0
Shuhua Cao | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 0 | 2 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 3; 2022-04-11: 3; 2022-04-12: 3; 2022-04-14: 2; 2022-04-19: 2; 2022-04-20: 2; 2022-04-21: 3; 2022-04-22: 1; 2022-04-25: 3; 2022-04-26: 2; 2022-04-27: 3; 2022-04-28: 2; 2022-04-29: 1; 2022-05-02: 4 | 3 | 3 | 3 | 1 | 3 | 4 | 3 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0
Sudhanshu Upadhye | 3 | 3 | 1 | 3 | 3 |  |  | 3 | 0 | 3 |  | 3 |  | 1 | 1 | 1 | 3 | 2 | 2022-03-16: 3; 2022-03-18: 3; 2022-03-20: 3; 2022-03-21: 3; 2022-03-23: 3; 2022-03-25: 3; 2022-04-06: 3; 2022-04-08: 2; 2022-04-11: 2; 2022-04-12: 1; 2022-04-14: 1; 2022-04-19: 1; 2022-04-20: 3; 2022-04-21: 1; 2022-04-22: 1; 2022-04-25: 1; 2022-04-26: 2; 2022-04-27: 3; 2022-04-28: 2; 2022-04-29: 3; 2022-05-02: 4 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 0 | 0 | 3 | 3 | 4 | 4 | 0
[19 empty] | 2022-05-02: Report writing week | [11 empty] | Testing and Implementation week at Hotel
Program Integration week
COVID outbreak
Note on Q9: Author: Job Interview
Note on M10: Author: No reason
Note on R10: Author: Did not want to wake up since drank the day before
Note on S10: Author: No reason
Note on O13: Author: Vacations
Note on P13: Author: Vacations
Note on Q13: Author: Vacations

## Champions
Champions
Name | Role | Responsibilities
Manideep Reddy | Report correct format | *Ensure the correct overall format of the report file according to the template provided by the University -References -Lettering -Figures and tables
Balaji Vedal | Wednesday Weekly MoMs | *Ensure the recording of the Minutes of Meeting (MoM) for the Wednesday Weekly meetings with the course director -Record the minutes of the weekly meetings with course director -Share the minutes with the team and the course Director
Shuhua Cao | GitHub | *Ensure the creation of GitHub and provide learning resources for the team. -Create the Git Hub site -Provide the team with basic training about GitHub. -Record the activities of the team.
Sudhanshu Upadhye | Lab Scheduler | *Ensure the scheduling of the Lab for the team to work with the Robot Platform. -Mail to coordinate with the Lab head to ensure an available slot for the team work. -Provide the team with access to the lab and coordinate the activities for the team. -Record minutes of meeting from the Lab visits
Krishna Mote | Logistics and Transportation | *Ensure the transportation availability for the team. -Booking taxi on time for a team from University-Hotel-University. -Keeping records of all kinds of bills of team. -Ensure the getting of reimbursement of all bills of the team’s expenditure from university.

## Ecalation Notice (hidden)
Escalation Notice
Group 5 - TIAGo Robot
Risk: | 1.Project timeline at risk 2.Project quality at risk 3. Team motivation at risk.
Problem Description: | 1. Some team members have not been assisting to the meetings as agreed. Consequently, the activities have been delayed. 2.1 Some team members are not working according to the team agreed deadlines. Consequently, the activities are done last minute with poor quality. 2.2 The lack of engagement of some team members is likely to hinder the quality of the overall project. 3. The members who are assisting to the meetings, and working on the project start to loose motivation. There is a feeling of unfairness as some team members need to dedicate more time in the project to make it work while some other members have part-time jobs or holidays.
Actions Taken | 1. Extraordinary meetings scheduled to meet the required deadlines. 1.1 Allocation of more work among the available team members to cover up for the missing tasks. 2. Increase of non-value-added management tasks to peer review other team members activities to ensure task quality. 3.1 Increase of non-value-added management tasks to record progress and differentiate the performance of team members. 3.2 Increase of team motivational talks/ discussion (taking time from meetings) to remind of the responsibilities of each member of the team.
Support Requested | 1. Include this point in next weekly meeting. 2. Discuss the team members reasons to be absent during the meetings, and ask team members for a priority list regarding their activities (Group project, Part time jobs, holidays, late sleeping, partying during the week) 3. Provide a required weekly hour work rate (e.g. 30 hours a week) for all team members which would like to remain involved in the group project. 4. Provide the team with a solution regarding eleven workload, and uneven available time during the week (individual grades / team re-structuring / individual project for some team members).

## System Team
System Team
Name | Role | Area | Sub-System | System Element | Responsibilities | Next Steps
Balaji Vedal | Design Engineer | Software | Navigation | Path Planning & Path Generation | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Deploy autonomous navigation simulation on Gazebo and RViz / Done 5. Connect to TIAGo robot in lab using ROS / Due 29.03.2022 6. Deploy a node on the TIAGo robot in lab / Due 29.03.2022 7. Map the AIRC lab and localise the robot
Jonathan Arreola | Systems Engineer / Design Engineer | Software | Human Robot Interaction | Robot Arm, Torso, Head, lights | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Deploy a pre defined command in TIAgo using the terminal / due: 3.22.23 5. Learn how to connect with PAL TIAGo (Physical Platform)/ due: 3.22.24 6. Deploy a predefined command in PAL TIAGo (Physical Platform) / due: 3.22.25 7. Write a bespoke arm/torso/head path and deploy in the simulation / due: 3.28.24 8. Write a bespoke arm/torso/head path and deploy in the (Physical Platform) / due: 3.28.28 --> Problem to deploy C++ files. It was done in Phyton.
Krishna Keshav | Design Engineer | Software | Navigation | Path Planning & Path Generation | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Start PAL TIAGo in lab / Due 25.03.2022 5. Deploy autonomous navigation simulation on Gazebo and RViz / Done 6. Connect to TIAGo robot in lab using ROS / Due 29.03.2022 7. Deploy a node on the TIAGo robot in lab / Due 29.03.2022 8. Deploy a path planning algorithm in simulation / Due 29.03.2022 9. Test different path planning algorithms in simulations / Due 06.04.2022 10. Deploy a path planning algorithm onto TIAGo robot in lab / Due 06.04.2022
Kshitij Raje | Design Engineer | Software | Human Robot Interaction | Speech Recognition | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Check the PAL TIAGo functionality and predefined TTS outputs (The Actual Robot) /due 21.03.22 5. Access TTS in Webcommander using Ubuntu Terminal /due 28.03.22 6. Run Basic commands like 'Hello' on TiaGo robot using Ubuntu Terminal /due 3.28.22 7. Find how to connect Google Speech API and Acapela nodes on ROS /due 28.03.22 8. Run the Hotel Receptionist script on PAL TIAGo using program/Ubuntu terminal /due 29.03.22 9. Try to implement Google speech API on PAL TIAGo in similar way and run basic commands like Move in a certain direction and Stop /due 5.4.22 10. Using NLP and Google speech API, make PAL TIAGo respond with its basic TTS answers in Simulation /due 06.04.22 11. Implement step 11 on real robot PAL TIAGo (Yuuni) /due 08.04.22
Manideep Reddy | Design Engineer | Software | Navigation | Computer Vision & SLAM | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Startup the Tiago (physical world) 5.use web commander interface/Controller to access the TIago 6. Get root access of the Tiago 7. Get the List of Nodes in ROS of tiago 8. Get the RQT graphs of the nodes of the ROS on TIago (physical ) 25/03/22 9. Deploy the navigation node and visualize the sensor data. 25/03/22 10. Deploy predicted Navigation Stacks on the real robot 25/03/22 11. Understand the difficulties between the real and theoretical 28/03/22
Shuhua Cao | Design Engineer | Software | Navigation | Object Detection & SLAM | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Go through the TIAGo ROS architecture 03/25/2022 5. Research and deploy the detection algorithms which includes the functions: 03/28/2022 Human detection, Human avoidance, Navigation to / away from human 6. Research and deploy the SLAM, achieve the environment construction by robot RGB-D camera. 03/31/2022
Sudhanshu Upadhye | Design Engineer | Software | Human Robot Interaction | Text to Speech | *Develop next steps list *Brief the team with the next steps *Present advance report | 1.Install ROS TIAGo workspace in Ubunto/ due: 3.21.22 2. Deploy ROS Gazebo Simulation in computer / due: 3.21.22 3. Deploy Gazebo Simulation for TIAGo and tun simple node to run in TIAGo/ due: 3.21.22 4. Check the PAL TIAGo functionality and predefined TTS outputs (The Actual Robot) /due 21.03.22 5. Search Google Speech API packages in ROS /due 23.03.22 6. Run Basic commands like 'Hello' on TiaGo robot using Ubuntu Terminal /due 3.25.22 7. Find how to connect Google Speech API and Acapela nodes on ROS /due 25.03.22 8. Check how the Google Speech API can be implemented on mobile robots /due 25.03.22 9. Try to implement Google speech API on PAL TIAGo in similar way and run basic commands like Move in a certain direction and Stop /due 30.3.22 10. Using NLP and Google speech API, make PAL TIAGo respond with its basic TTS answers in Simulation /due 06.04.22 11. Implement step 11 on real robot PAL TIAGo (Yuuni) /due 08.04.22
Safety (All)

## Hotel Visit
Group 5
Attendee | Assisting?
Balaji Vedal | Yes
Jonathan Arreola | Yes
Krishna Keshav | Yes
Kshitij Raje | Yes
Manideep Reddy | Yes
Shuhua Cao | Yes | `
Sudhanshu Upadhye | No
Total attendees | 6

## Contribution Table
Name | Management | Technical | Coding | Report | Presentation
Balaji Vedal | Role: Wednesday Weekly MoMs champion Activities: *Ensured the recording of the Minutes of Meeting (MoM) for the Wednesday Weekly meetings with the course director -Recorded the Minutes of the Weekly meetings with course director -Shared the Minutes with the team and the course director | - Performed robot Localization. - Performed robot waypoint creation - Performed problem solving activities for navigation - Created Matlab MSym architecture file - ROS learning. | - supported coding for Kinematics, navigation. | - [ ] Abstract - [ ] Introduction (customer satisfaction, resource management, staff retaining - [ ] Lit review Robot Platform TIAGo(4.2): General Review(4.2.1) - [ ] Lit review Tasks(4.3): Path planning (4.3.1) - [ ] Lit review text to Speech(4.3.6) - [ ] System system architecture 5.1.4.2 MATLAB System Composer - [ ] Detailed design 5.1.7 : ROS Basics 5.1.7.1 Messages - [ ] 5.1.7.2 basics of PAL TIAGo Introduction and startup/shutdown - [ ] 5.1.7.4 Running code in real robot introduction and accessing the physical robot and running code through terminal sensor visualisation, navigation, mapping, localisation - [ ] 5.1.10 Implementation | - Created final group presentation. - Performed photography activities for the presentation and team record. - Recording activities for team presentation and record.
Jonathan Arreola | Role: Project Manager Activities: *Ensured the delivery of the project in time and form. - Planned project structure and timeline. - Created and updated the gantt chart and milestones. - Delegated management activities and ensured the proper execution of the same. - Kept record of the team assistance and activities. - Programmed team meetings through outlook invitations. - Recorded Minutes of the Meeting for team meetings. - Provided learning resourced for team members. - Main point of contact with the PAL development team for problem solving. - Main point of contact for stakeholders of the project. - Supported team members through technical development. | -Assisted problem solving management activities. | - Coded Human Robot Interaction System node. Kinematics: Robot arm, head, torso, movements. Text to Speech: predefined phrases. - Contributed to code Navigation System node. - Coded integrated node for overall program execution. Kinematics, Text to Speech, Navigation. | 2. Literature Review
Krishna Keshav | Role: Logistics and Transportation champion / Task managment for navigation devlopment Activities: *Ensure the transportation availability for the team. -Booking taxi on time for a team from University-Hotel-University. -Ensure the reimbursement of all bills for the team’s expenditure from university. | - Performed robot Localization. - Performed robot waypoint creation - Performed problem solving activities for navigation | - supported coding for navigation. | Acknowledgment 1. Introduction 2. Objective 4. Literature Review Introduction 4.2 SMART Cities 4.2.1 Milton Keynes - Smart City(MK:Smart) 4.4.1 Navigation and Path Planning 4.4.1.1 State of the art or current approaches 5.1.3 Functional Analysis 5.1.7.1 ROS Basics- Node 5.1.7.2 Basics of PAL TIAGo - Perform movements with the Web Commander GUI Running code through terminal in simulation (Gazebo / RViz ) - Introduction Running code through terminal in simulation (Gazebo / RViz ) - Navigation Subsystem Running code through terminal in Real Robot - Mapping Running code through terminal in Real Robot - Localisation | - Assisted the final group presentation. - Participated in visual presentation activities. - Recording activities for team presentation and record.
Kshitij Raje | - |  | - Coded Speech recognition interactive node --> Remark: (late delivery. Not able to integrate with final program).
Manideep Reddy | Role: Report correct format champion / Assisted with team engagement Activities: *Ensured the correct overall format of the report file according to the template provided by the University. -References -Lettering -Figures and tables | - Performed robot Localization. - Performed robot waypoint creation - Performed problem solving activities | - Contributed to code Navigation System node. |  | - Assisted the final group presentation - Perfomed computer vision simulation. - Recording activities for team presentation and record.
Shuhua Cao | Role: GitHub champion Activities: *Ensured the creation of GitHub and provide learning resources for the team. -Created the Git Hub site and maintained it. -Provided the team with basic training about GitHub. - Created detailed read me files for the group repository. - Performed version management for the team code. | - Performed robot Localization. - Performed robot waypoint creation - Performed problem solving activities - Contributed for Matlab MSym architecture file | - Coded Navigation System node. |  | - Participated in visual presentation activities.
Sudhanshu Upadhye | Role: Lab Scheduler Activities: *Ensure the scheduling of the Lab for the team to work with the Robot Platform. -Mail to coordinate with the Lab head to ensure an available slot for the team work. -Provide the team with access to the lab. -Record minutes of meeting from the Lab visits --> Remark: commited, but did not performed this activity. |  | - Coded Speech recognition interactive node --> Remark: (late delivery. Not able to integrate with final program).