## Slide 1
2022
2022
System Preparation
Literature Review
System. Definition
System. Detailed Design
System. Testing
System Impementation
Today
Feb
Mar
Apr
May
2022
4 days
Feb 28 - Mar 4
Operative system installation
3 days
Mar 3 - Mar 8
ROS installation
23 days
Mar 3 - Apr 5
ROS Learning
5 days
Mar 8 - Mar 14
Working Environment
5 days
Mar 8 - Mar 14
Robot platform. Hardware & Software
5 days
Mar 8 - Mar 14
Navigation. Path planning & Object Detection
5 days
Mar 8 - Mar 14
HRI. Kinematics & Speech
7 days
Mar 15 - Mar 23
Stake holders' statement & Concept definition
16 days
Mar 15 - Apr 5
System Architectire
7 days
Mar 15 - Mar 23
System SOR
43 days
Mar 22 - May 12
Simulation Testing
7 days
May 02 - May 12
Physical Testing
Robot Deployment
May 12
2 days
Mar 18 - Mar 22
TIAGo Basics Learning
7 days
Mar 22 - Mar 31
TIAGo Control by devmnt Computer
10 days
Mar 22 - Apr 5
TIAGo Bespoke Program
24 days
Apr 15 - Apr 28
TIAGo Program Integration
Hotel Visit
Mar 14
Testing at Hotel
Apr 18
Project Kickoff
Feb 28
Stadium Robotics Project Progress review
Apr 6
Literature Review Completion
Mar 17
Physical Testing at Hotel
Apr 22
Final Implementation
May 12
Today